56

University Advancement

Corporate and Foundation Relations, Pre-funding Support

Three Week Proposal Preparation Timeline

Principal Investigator (PI, Faculty or Staff member):

Funding Opportunity:

| Completed | Action Item | Date Due |
| --- | --- | --- |
|  | WEEK ONE – Research and Coordination |  |
| ☐ | PI sends CFR0F Director information on the foundation (if applicable); and requested areas for funding: travel, materials, staffing, student assistants, course release, summer pay, overload pay, other. |  |
| ☐ | PI notifies Dean and School Director/Department Chair of the intent to submit a proposal for funding. |  |
| ☐ | CFR Director reaches out to foundation contact to determine if project is a good fit (if applicable) |  |
| ☐ | PI discusses writing and editing needs with College Development Liaison and CFR Director. |  |
|  | WEEK TWO – Writing and Editing |  |
| ☐ | PI sends CFR Director draft narrative, budget and budget justification. |  |
| ☐ | PI confirms Dean and/or School Director approval and support of proposal with email indicating approval or signature at bottom checklist here. |  |
| ☐ | CFR Director sends edits to PI for review and finalizing proposal and budget. |  |
| ☐ | PI sends final narrative, budget and budget justification to CFR Director. |  |
|  | WEEK THREE – Approval and Submission |  |
| ☐ | Complete internal approval process (review and signature of University Advancement Vice President and PI’s Department) with assistance from CFR Director. |  |
| ☐ | PI and CFR Director assemble proposal application. |  |
| ☐ | PI and CFR Director review final application and submit. |  |
| ☐ | CFR Director and/or PI monitor email messages for proposal submission confirmation or requests for additional follow-up. |  |

Please note, if you are unable to meet a due date as listed, immediately contact CFR staff or your College’s Development Liaison to avoid possibly jeopardizing your proposal submission. For any questions please contact, Christine Andersen at candersen@csusum.edu, x 7310

Approval signature from Dean/Leadership

Corporate and Foundation Relations (CFR)